## Summary
6
Progress: | 83.33%
Passed: | 16.67%

## Test Suite
Project: 2022-2023-project-5-algorithmitcs-Team-7
Test cases
Product Area | ID | Feature | Priority | Assignee | Expected Results | Status | Link to test cases
Documents | 1 | Project Charter | High | Thomas | Complete document to initialize the project including information about the scope of the project, the goal of the project, the client, the team, budget, risk and acceptance criterias. | Pass
| 2 | Functional Specifications | High | Karine | Complete document with all necessary informations for the Tech Lead to create the Technical Specifications and the Architecture Diagram, and for the Quality Assurance to create the Test Plan. | Fail | https://docs.google.com/spreadsheets/d/1uCJrfU7ePSEYzvzTxc2P3sQFFSlSrLOx6Xyt8DMNn74/edit?usp=sharing
| 3 | Technical Specifications | High | Christopher | Complete document with all the necessary informations for the Software Engineer to create the final product. | In Progress
| 4 | Risk Management Plan | Medium | Quentin | Complete document containing identification, assessment and prioritization of potential risks associated with the software system, including plans to mitigate or avoid these risks and help ensure controlled and predictable testing. | Not Started Yet
| 5 | Deployment Plan | Medium | Christopher | Complete document containing effective and efficient testing to verify proper installation and configuration, setting up the environment appropriately and managing potential risks at the time of deployment. | Not Started Yet

## Utility
Person | Mail | Status | Priority
Thomas | thomas.planchard@algosup.com | Pass | High
Karine | karinevinette@orange.fr | Fail | Medium
Christopher | cdiggins@gmail.com | In Progress | Low
Léo | leo.chartier@algosup.com | Not Started Yet
Quentin | quentin.clement@algosup.com

## Progress History
Data | Progress | Remaining Tests
01.03.2018 | 10% | 90%
02.03.2018 | 35% | 65%
05.03.2018 | 45% | 55%
06.03.2018 | 55% | 45%
07.03.2018 | 90% | 10%

## History by Builds
Version | Found issues |  |  | Data | Passed
| Critical | Major | Minor
1.0.1 | 4 | 5 | 1 | 15.01.2018 | 30%
1.0.2 | 3 | 3 | 0 | 05.02.2018 | 60%
1.0.3 | 1 | 0 | 2 | 01.03.2018 | 85%
1.0.4 | 0 | 0 | 1 | 14.03.2018 | 100%